## W1
WEEKLY REPORT
Group | 3
Week | <11/05/2026-17/05/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Collect software requirement | Every Member | Completed | Đến trực tiếp nhà xe để hỏi
2 | Start SRS documentation | Every Member | In Progress
3 | Decide project techstacks | Every Member | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Proceed to draw ERD and Usecase Diagram | Everyone | 2026-05-23
2 | Setup initial project on github | Đoàn Ngọc Đức | 2026-05-23
3 | Continue to make SRS document | Everyone | 2026-05-23
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W2
WEEKLY REPORT
Group | 3
Week | <18/05/2026-24/05/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Proceed to draw ERD and Usecase Diagram | Everyone | Completed
2 | Setup initial project on github | Đoàn Ngọc Đức | Completed
3 | Continue to make SRS document | Everyone | Pending
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Continue to make SRS document | Everyone | 2026-05-30
2 | Proceed to database design | Everyone | 2026-05-30
3 | Divide module to member | Đoàn Ngọc Đức | 2026-05-26
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W3
WEEKLY REPORT
Group | 3
Week | <25/05/2026-31/05/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Continue to make SRS document | Everyone | In Progress
2 | Proceed to database design | Everyone | Completed
3 | Divide module to member | Everyone | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Make SDS Document | Everyone | 2026-06-06
2 | Code HomePage and Search Trip | Đoàn Ngọc Đức | 2026-06-06
3 | Code Register and Login | Phan Đức Trung | 2026-06-06
4 | Code Coach Type & Coach CRUD | Lê Thu Hà | 2026-06-06
5 | Coach Route & Coach Stop CRUD | Nguyễn Minh Thành | 2026-06-06
6 | Code Cargo Type CRUD | Trần Trọng Hiếu | 2026-06-06
7 | Code Voucher CRUD | Tuấn Hưng | 2026-06-06
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W4
WEEKLY REPORT
Group | 3
Week | <01/06/2026-07/06/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Make SDS Document | Everyone | Completed
2 | Code HomePage and Search Trip | Đoàn Ngọc Đức | In Progress
3 | Code Register and Login | Phan Đức Trung | In Progress | Le Thu Ha joined to make the rework
4 | Code Coach Type & Coach CRUD | Lê Thu Hà | Completed
5 | Coach Route & Coach Stop CRUD | Nguyễn Minh Thành | In Progress
6 | Code Cargo Type CRUD | Trần Trọng Hiếu | In Progress
7 | Code Voucher CRUD | Tuấn Hưng | In Progress | Member quitted
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Code HomePage and Search Trip | Đoàn Ngọc Đức | 2026-06-13
2 | Code general Auth features | Lê Thu Hà | 2026-06-13 | Doan Ngoc Duc helped with JWT-related transaction added in
3 | Code Voucher CRUD | Phan Đức Trung | 2026-06-13
5 | Coach Route & Coach Stop CRUD | Nguyễn Minh Thành | 2026-06-13
6 | Code Cargo Type CRUD | Trần Trọng Hiếu | 2026-06-13
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W5
WEEKLY REPORT
Group | 3
Week | <08/06/2026-14/06/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code HomePage and Search Trip | Đoàn Ngọc Đức | Completed
2 | Code general Auth features | Lê Thu Hà | Completed | Doan Ngoc Duc helped with JWT-related transaction added in
3 | Code Voucher CRUD | Phan Đức Trung | Completed
4 | Coach Route & Coach Stop CRUD | Nguyễn Minh Thành | Completed
5 | Code Cargo Type CRUD | Trần Trọng Hiếu | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Code Trip Scheduling | Đoàn Ngọc Đức | 2026-06-20
2 | Code Cargo Type CRUD | Trần Trọng Hiếu | 2026-06-20
3 | Code Ticket Booking (Customer Site) | Lê Thu Hà | 2026-06-20
4 | Code Payment Transaction | Nguyễn Minh Thành | 2026-06-20 | Build the payment transaction using SePay webhook for Ticket Booking module.
5 | Code System Admin features | Phan Đức Trung | 2026-06-20
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W6
WEEKLY REPORT
Group | 3
Week | <15/06/2026-21/06/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code Trip Scheduling | Đoàn Ngọc Đức | In Progress
2 | Code Cargo Type CRUD | Trần Trọng Hiếu | In Progress
3 | Code Ticket Booking (Customer Site) | Lê Thu Hà | In Progress
4 | Code Payment Transaction | Nguyễn Minh Thành | Completed
5 | Code System Admin features | Phan Đức Trung | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Code Cargo Type CRUD | Trần Trọng Hiếu | 2026-06-27
2 | Code Ticket Booking (Customer Site) | Lê Thu Hà | 2026-06-27
3 | Code System Admin features | Phan Đức Trung | 2026-06-27
4 | Code Trip Scheduling | Đoàn Ngọc Đức | 2026-06-27
5 | Code Cargo Management feature | Nguyễn Minh Thành | 2026-06-27
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W7
WEEKLY REPORT
Group | 3
Week | <22/06/2026-28/06/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code Cargo Type CRUD | Trần Trọng Hiếu | In Progress | Member quitted due to skill issue
2 | Code Ticket Booking (Customer Site) | Lê Thu Hà | Completed | Doan Ngoc Duc helped with email setup for sending confirmation
3 | Code System Admin features | Phan Đức Trung | Completed
4 | Code Trip Scheduling | Đoàn Ngọc Đức | Completed
5 | Code Cargo Management feature | Nguyễn Minh Thành | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Code Cargo Type CRUD | Đoàn Ngọc Đức | 2026-07-04
2 | Code Cargo Management feature | Nguyễn Minh Thành | 2026-07-04
3 | Code Trip Staff features | Phan Đức Trung | 2026-07-04
4 | Code Passenger Ticket Management features | Lê Thu Hà | 2026-07-04
5 | Code Customer Profile, Customer History features | Đoàn Ngọc Đức | 2026-07-04
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W8
WEEKLY REPORT
Group | 3
Week | <29/06/2026-05/07/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Code Cargo Type CRUD | Đoàn Ngọc Đức | Completed
2 | Code Cargo Management feature | Nguyễn Minh Thành | In Progress
3 | Code Trip Staff features | Phan Đức Trung | In Progress
4 | Code Passenger Ticket Management features | Lê Thu Hà | Completed
5 | Code Customer Profile, Customer History features | Đoàn Ngọc Đức | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Finish remaining docs | Everyone | 2026-07-11
2 | Code Cargo Management feature | Nguyễn Minh Thành | 2026-07-11
3 | Code Trip Staff features | Phan Đức Trung | 2026-07-11
4 | Code Refund feature for Passenger Ticket | Lê Thu Hà | 2026-07-11
5 | Code View Trip for Ticket Staff, Forgot password for Staff site | Đoàn Ngọc Đức | 2026-07-11
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W9
WEEKLY REPORT
Group | 3
Week | <13/07/2026-19/07/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Finish remaining docs | Everyone | In Progress
2 | Code Cargo Management feature | Nguyễn Minh Thành | Completed
3 | Code Trip Staff features | Phan Đức Trung | Completed
4 | Code Refund feature for Passenger Ticket | Lê Thu Hà | Completed
5 | Code View Trip for Ticket Staff, Forgot password for Staff site | Đoàn Ngọc Đức | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
1 | Finish remaining docs | Everyone | 2026-07-25
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W10
WEEKLY REPORT
Group | 3
Week | <20/07/2026-26/07/2026>
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Finish remaining docs | Everyone | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Task | In-charge | Deadline | Notes (Task Details, etc.)
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes